## Slide 1
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW
SLIDE 1
RICH MODULE INTEGRATION IN CLAS_12 – LAST LAYOUT
RICH MODULE

## Slide 2
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: RICH INTEGRATION IN CLAS_12 STATUS
TOF REGION_1
BEAM PIPE
SLIDE 2
CHECKING OF INTEGRATION OF THE RICH MODULE IN CLAS_12, HAS BEEN DONE , IN COLLABORATION WITH THE JLAB ENGINEERING SERVICE.
DRIFT CHAMBERS
RICH MODULE

## Slide 3
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: RICH INTEGRATION IN CLAS_12 STATUS
RIGHT HOOKING STIRRUP
SLIDE 3
THE BEAM PIPE HOOKING COLLAR POSITION WILL BE DEFINED BY JLAB E_SERVICE IN JULY 2015
THE HOOKING STIRRUPS POSITION WILL BE DEFINED BY JLAB E_SERVICE IN JULY 2016 (+/-10mm).
SLOTS WILL BE PROVIDED INSTEAD OF HOLES .
LEFT HOOKING STIRRUP
BEAM PIPE HOOKING COLLAR
TOPICS UNDER DEVELOPMENT

## Slide 4
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: RICH SUPPORT STRUCTURE STATUS
SLIDE 4
TENDER STARTED IN DECEMBER 2014
TENDER INVITATION S ENT TO THE FIRMS IN APRIL 2015
TENDER ASSIGNED IN MAY 2015
ADMINISTRATIVE PROCEDURE COMPLETED
CONSTRUCTION ALREADY STARTED
ASSEMBLY TEST FOR DECEMBER 2015
DELIVERED AT JLAB PLANNED FOR MARCH 2016
RICH SUPPORT STRUCTURE TENDER

## Slide 5
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: RICH SUPPORT STRUCTURE STATUS
LATERAL PLATE
(ALUMINUM SKINS PLUS HONEYCOMB CORE)
TOP PLATE
(ALUMINUM ALLOY)
LOWER PLATE
(ALUMINUM ALLOY)
FRAME FOR E_PANEL
(CFRP)
SLIDE 5
RICH SUPPORT STRUCTURE
(FRONT VIEW)
LATERAL PLATE
(ALUMINUM SKINS PLUS HONEYCOMB CORE)
FRAME FOR FRONTAL PANEL
(CFRP)
4200mm
3650mm
270mm
1150mm

## Slide 6
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: RICH MODULE STATUS
LATERAL PLATE
(ALUMINUM SKINS PLUS HONEYCOMB CORE)
TOP PLATE
(ALUMINUM ALLOY)
CABLES RACEWAYS
(ALUMINUM ALLOY)
FRAME FOR E_PANEL
(CFRP)
LATERAL PLATE
(ALUMINUM SKINS PLUS HONEYCOMB CORE)
CABLES RACEWAYS
(ALUMINUM ALLOY)
FRAME FOR BACKWARD PANEL
(CFRP)
SLIDE 6
RICH SUPPORT STRUCTURE
(REAR VIEW)
LATERAL FRAME
(ALUMINUM ALLOY 23mm Thickness)
CENTRAL CORE
ALUMINUM HONEYCOMB 23mm Thickness
(IN YELLOW)

## Slide 7
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: RICH SUPPORT STRUCTURE STATUS
OUTER FRAME: MONOLITIC CARBON FIBER
CENTRAL ZONE: NOMEX HONEYCOMB (ARAMID FIBER)
SKINS: CFRP
SLIDE 7
TOP PANEL UPDATE
PREVIOUS VERSION
NEW SOLUTION PROPOSED BY TECNAVAN
TOP PLATE
(ALUMINUM ALLOY: 130 Kg)
CENTRAL CLOSING PANEL
(NOMEX HONEYCOMB: 10 Kg)
TOTAL WEIGHT: 140Kg
TOTAL WEIGHT: 80Kg
MATERIAL BUDGET GAIN:
FROM 17.4% X_0 TO 9.0% X_0

## Slide 8
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: RICH SUPPORT STRUCTURE STATUS
SERVICES BALCONIES
ASSEMBLY STRUCTURE
SLIDE 8
RICH MODULE
TOGHETER WITH THE TENDER OF THE RICH SUPPORT STRUCTURE, HAS BEEN ASSIGNED ALSO THE REALIZATION OF THE “RICH MODULE ASSEMBLY STRUCTURE”
IT ‘S NECESSARY TO THE ASSEMBLY OF THE RICH
RICH MODULE ASSEMBLY STRUCTURE

## Slide 9
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: RICH SUPPORT STRUCTURE STATUS
SLIDE 9
ROTATION STEP_1
ROTATION STEP_2
ROTATION STEP_3
TROLLEY
THE RICH HAS BEEN ASSEMBLED
THE RICH IS ROTATED BY THE CRANE
THE RICH IS PLACED ON A TROLLEY
THE TROLLEY IS MOVED OUT OF THE ASSEMBLY ROOM
- RICH MODULE ROTATION STEPS

## Slide 10
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: RICH SUPPORT STRUCTURE STATUS
SLIDE 10
TROLLEY FOR MOVING RICH MODULE
TROLLEY
RICH MODULE
TWO HYPOTESIS ARE UNDER DISCUSSION:
A) TO REALIZE A TROLLEY SUITABLE ONLY FOR MOVING OUT THE RICH OUTSIDE
THE CLEAN ROOM. THEN, BY THE HALL CRANE IT WILL BE PLACED ON A TRUCK
AND CARRIED IN HALL B.
B) TO REALIZE A TROLLEY SUITABLE TO CARRY THE RICH FROM THE CLEAN
ROOM , DIRECTLY TO THE HALL B, TOWED BY AN ELECTRIC FORKLIFT.
A DEDICATED TROLLEY IS UNDER DEVELOPMENT TO OPTIMIZE THE MOVING OF THE RICH MODULE

## Slide 11
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: RICH SUPPORT STRUCTURE STATUS
SLIDE 11
A TRIPOD FOR LIFTING RICH MODULE
LIFTING TRIPOD
RICH MODULE
A TRIPOD FOR RIGGING THE RICH MODULE INSIDE THE FORWARD CARRIAGE IS UNDER DEVELOPMENT
BASICALLY IS THE SAME TOOL USED TO RIGGING THE LTCC MODULE.
THE ARMS OF HOOKING (GEOMETRY AND STIFFNESS) HAVE BEEN MODIFIED
ARMS OF HOOKING

## Slide 12
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: FRONTAL PANEL STATUS
SLIDE 12
1° FLAT MIRRORS PLUS
AEROGEL TILES 20mm IN THICKNESS
2° FLAT MIRRORS PLUS
AEROGEL TILES 20mm IN THICKNESS
AEROGEL TILES 30+30mm=60mm
IN THICKNESS (NO MIRROR)
SUPPORT PANEL
- 2 SKINS (CFRP)
- NOMEX HONEYCOMB CORE
MIRRORS:
- 2 GLASS SKINS 0.7mm IN THIKNESS
- ALUMINUM HONEYCOMB CORE
FRAME 40x10-1mm (ALUMINUM)
SUPPORT (ABS)

## Slide 13
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: E_PANEL STATUS
SLIDE 13
HEIGHT 1270mm
1680mm
350mm
2 PMT’s TILES
(IN YELLOW)
E_PANEL MAIN NUMBERS:
- 391 PMTs
- 23 LAYERS
(1° LAYER > 6 PMTs)
(23° LAYER > 28 PMTs)
- 2 PMTs TILES: 23 > 23x2= 46 PMTs
- 3 PMTs TILES: 115 > 115x3= 345 PMTs
(-3 PMTs TILES HAVE BEEN PREFERRED)
3 PMT’s TILES
(IN ORANGE)

## Slide 14
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: E_PANEL STATUS
SLIDE 14
3 PMT’s TILES
2 PMT’s TILES
THE SUPPORT PANEL IS MADE OF
2 ALUMINUM SKINS PLUS
ROHACELL OR HONEYCOMB CORE
OUTER FRAME
(ALUMINUM ALLOY)
SLOTS FOR HOUSING OF CONNECTORS
AREA SIMULATED WITH
PROTOTYPE

## Slide 15
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: E_PANEL STATUS
SLIDE 15
PMT’s TILES
CABLES RACEWAY
THE AIM OF THE PROTOTYPE IS:
- TO TEST THE MECHANICAL COUPLING
BETWEEN THE COMPONENTS;
- TO TEST THE LIGHT-TIGHT PERFORMANCES;
- TO TEST THE CABLING ROUTING.
PRELIMINARY RESULTS:
- COUPLING BETWEEN ADAPTER BOARD AND SUPPORT
PANEL … GOOD (BLACK PLASTIC SCREWS TO IMPROVE) ;
- COUPLING BETWEEN ADAPTER / ASIC / FPGA … PERFECT;
- LIGHT-TIGHT … GOOD BUT TO BE IMPROVE AROUND THE
HV CONNECTOR;
- CABLING ROUTING STILL TO DO.

## Slide 16
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: E_PANEL STATUS
SLIDE 16
ADAPTER BOARD
NEW SEAL
- THE NEW ONE WILL BE REALIZED:
- 1) NOT COMMERCIAL, BUT MADE DIRECTLY FROM OUR DESIGN
- 2) REALIZED IN TWO SOLUTIONS THAT WILL BE TESTED:
A) EPDM (FOAM)
B) VITON
A NEW SEAL IS UNDER DEVELOPMENT
ASIC BOARD
FPGA BOARD
OLD SEAL

## Slide 17
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: CABLING STATUS
SLIDE 17
E_PANEL ELECTRONIC BOARDS
CABLES
RACEWAY
- THE CABLES RACEWAYS ARE INTEGRATED ON THE
RICH SUPPORT STRUCTURE AND THEY ARE UNDER
CONSTRUCTION;
- THE INTEGRATION OF THE CONNECTORS WITH THE
PATCH PANELS IS UNDER DEVELOPMENT.
SCHEMATIC CABLES ROUTING

## Slide 18
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW: PATCH_PANELS STATUS (By Kevin Bailey – Argonne)
SLIDE 18
TOP PANEL
PATCH PANEL
THE P_PANELS ARE UNDER DEVELOPMENT BY AN ARGONNE COLLABORATION (K. Bailey)
- THE ACTUAL VERSION IS PLACED ON THE SIDES OF THE
TOP PANEL;
- DURING THE ASSEMBLING ON THE FORWARD CARRIAGE,
IT WILL BE ROTATE IN HORIZONTAL POSITION;
- THE CHECKING WITH THE “TOF REGION 2” HAS BEEN
MADE.

## Slide 19
INFN-LNF / D. Orecchini – S. Tomassini – 06/24-25/2015
CLAS12 – RICH MECHANICS REVIEW:BACKWARD PANEL STATUS (By Kevin Bailey – Argonne)
SLIDE 19
COMPONENTS STILL UNDER DEVELOPMENT ....
THE COOLING SYSYTEM OF THE HEAT PRODUCED BY THE ELECTRONICS OF THE E_PANEL IS UNDER DEVELOPMENT IN LNF
E_PANEL
BACKWARD PANEL (CFRP)
CHIMNEY FOR EVACUATION EXAUST AIR, ARE DIRECTLY BUILT IN THE BACKWARD PANEL
HOLES ON TOP PANEL FOR EVACUATION EXAUST AIR