## Slide 1
Hall B RICH Review
September 05+06, 2013
Readiness Review Process
Rolf Ent

## Slide 2
Readiness Review Process
Jefferson Lab experiments typically use a combination of base equipment and new, often JLab-user led and constructed, equipment.
How do we integrate such new equipment effectively and safely?
Outline:
Experimental Readiness Review Process in the 4 & 6 GeV era
Management self-assessment for "Installation of New Equipment Involving Multiple Groups”.
New Experimental Readiness Review Process in the 12 GeV era
Implications for RICH

## Slide 3: Experiment Systems Readiness Process - General
Experiment Systems Readiness reviews are standalone reviews required prior to delivery of any beam to the respective Hall. The Experiment Systems Readiness Process has been used effectively for all JLab experiments since the start of experiments in 1995.
Experiments went through different levels of readiness reviews depending
on being categorized as “Experiments using major new apparatus”.
Goal: assure that the equipment can be safely and effectively operated, and
to document operational procedures appropriate for its commissioning.
All 12-GeV equipment will undergo an Experiment Systems (Hall A, B, C,
and D) Readiness review as a modular piece of the overall Accelerator Readiness
Review (ARR) process.
Basic commissioning of components initiated under JLab Temporary
Operational Safety Procedures (Chapter 3320, “Temporary Work Permits”)
Checkout of full equipment with beam requires
    Conduct of Operations (COO)
    Radiation Safety Assessment Document (RSAD)
    Experimental Safety Assessment Document (ESAD)
    Safety Checklists

## Slide 4: Experiment Systems Readiness Process - Example
G0 Experiment in Hall C as example of “Experiments using major new apparatus”. Series of Equipment Readiness, Safety, and Documentation reviews during design & construction phases before operations.
target service
vessel
beam line
SC magnet
detectors

## Slide 5: G0 Safety and Technical Reviews (2002 only)
G0 Experiment in Hall C as example of “Experiments using major new apparatus”. G0 reviews in 2002, the year of final installation and commissioning (many more before th
Date | System | Scope | Reviewers
Feb. 11-12 | Target | Engineering & Safety Review | J. Kilmer (FNAL), J. Mark (SLAC), J. Domingo (JLab), D. Kashy (JLab), W. Vulcan (JLab), M. Seely (JLab)
May 01 | Magnet + Target | TOSP for Vacuum Evacuation | ESH&Q + Subject Matter Experts (SME)
May | Target | Punchlist Items Review | J. Domingo (JLab,), D. Kashy (JLab), W. Vulcan (JLab)
May | Target | TOSP Neon Test | ESH&Q + SME
May | Target | TOSP Hydrogen Cooldown | ESH&Q + SME
Jun. 24-25 | Magnet | Engineering & Safety Review | B. Schneider (JLab), A. Visser (FNAL), J. Gomez (JLab), A. Guerra (JLab)
July | Magnet | TOSP Magnet Cooldown | ESH&Q + SME
Aug. 09 | G0 | RSAD | ESH&Q (Radiation Control Group)
Aug. 14 | G0 | Full EH&S Review (I) (Last Readiness Review) | G. Dodson (ORNL), J.P. Chen (JLab), B. Manzlak (JLab), E. Smith (JLab), M. Spata (JLab), W. Vulcan (JLab)
Aug. 21 | G0 | TOSP G0 Beam Tests | ESH&Q + SME
Sep. 09 | G0 + Magnet | TOSP Powering of the G0 SMS and G0 Beam Tests | ESH&Q + SME
Sep. 16 | G0 | COO and ESAD | ESH&Q + SME
Sep. 19 | G0 | Full EH&S Review (II) (Last Readiness Review) | G. Dodson (ORNL), J.P. Chen (JLab), B. Manzlak (JLab), E. Smith (JLab), N. Okay (JLab), W. Vulcan (JLab)

## Slide 6
Experiment Systems Readiness Process - findings
Performed a Management Self-Assessment process at the end of the 6-GeV era to look at “Installation of New Equipment Involving Multiple Groups”.
Asked group to fold in experience of Hall C/Qweak and Hall A/g2p experiments, Hall B/HDICe, and earlier reports/lessons learned on for instance Hall C/HKS, Hall A/PREX, etc. Both staff and users were polled.
Two findings
Experiment Readiness Review Process has not been followed thoroughly for the last couple of projects
    Not well defined what constitutes an experiment with major new apparatus
    Readiness Review process and reviews should be clearly articulated
    Design changes were allowed until very (too) late
    Identification of beam and lab infrastructure requirements need to be done early
Experiment Readiness Review Process not commonly known
    Discrepancies in knowledge amongst Hall C vs. other Halls
    Discrepancies in knowledge amongst Physics Division vs. other Divisions
    Discrepancies in knowledge amongst Staff vs. Users
Two noteworthy practices
Roles and Responsibilities seemed to be well known.
The existing model seems to work well, with very good communication, coordination, and cooperation.

## Slide 7: Revised READINESS REVIEW PROCESS @ 12 GeV
Jefferson Lab has revisited the experimental readiness review process in preparation of the 12-GeV startup.
That means:
  Partly correcting the Experiment Readiness Review web pages
  Folding in feedback from the management self-assessment for "Installation of New Equipment Involving Multiple Groups”.
The document, expected to be officially released with the completion of the web pages, will give the guidance for running experiments in the 12 GeV era.

## Slide 8
DECOMMISSIONING
Submitting Proposals
TAC & PAC Process
Director’s Decision
PROPOSAL PHASE
PRELIM. PLANNING PHASE
Exp. Description and Requirements
Exp. Readiness Review Calendar

DESIGN PHASE

PESAD, specific equipment reviews
Complete Conceptual Designs & “1st” Readiness Review

CONSTRUCTION PHASE
Fabrication of the equipment
Test of the individual elements of the equipment (OSP/TOSP)
SCHEDULING OF EXPERIMENT
by JLab
EQUIPMENT INSTALLATION

RUN THE EXPERIMENT
“Final” readiness review
Final ESAD & RSAD
COO
Safety Checklist(s)
Experimental Procedures
Construction near-completed, designs frozen
“2nd” Readiness Review before submitting scheduling request
Readiness Review Process – Flow Chart

## Slide 9
Readiness Review Process – Web Pages
http://www.jlab.org/user_resources/PFX/NP-PFX/
Or as text only version:
http://www.jlab.org/user_resources/PFX/NP-PFX/text.html

## Slide 10
By the spokespersons

## Slide 11
By the Division Safety Officer

## Slide 12: ESH&Q Integration for RICH in Physics
Fully integrate ESH&Q into planning and design
  Perform hazard analysis for new scope
    No hazard found requiring PESAD/1st readiness review of RICH
  Coordination of work with outside institutions
  Design and safety reviews of major subsystems
    Prepare for “2nd” readiness review stage before scheduling request
    Integration of assembly and commissioning tasks
  Design changes where appropriate, e.g.,
    No flammable gases, environmental-friendly where possible
    Reduce voltage where possible
Freeze design after “2nd readiness review” to prevent surprises for installation and running.

## Slide 13: “Final” READINESS REVIEW
Concentrates on ESH
Final readiness documents for experiments include:
    Conduct of Operations (generic for all Halls, A-D)
    Experiment Safety Assessment Documents
    (<40 page document of generic form)
    Radiation Safety Assessment Documents (no changes)
    Safety Checklists
    Experimental Procedures (these are for the users, they can be on wikis or as “one-pagers” in the Hall documentation)
Includes planning for decommissioning, if applicable
We plan to independently construct an “Operations Manual” for experts that simply links all TOSPs used for commissioning the new equipment – the RICH would be folded in here.
RICH can be declared “base equipment” only by the Division Safety Officer

## Slide 14
Readiness Review Process - Summary
The Experiment Systems Readiness Process has been used effectively
for all JLab experiments since the start of experiments in 1995
The existing model seems to work well, with very good communication, coordination, and cooperation amongst multiple divisions, and
    roles and responsibilities well defined (work coordinator, physics liaison, accelerator liaison, engineering coordinator)
Nonetheless, the process was not well known and not always followed
Revisited experiment systems readiness process to
    Clarify review process from the start – communicated to users
    Update web pages for consistency – in progress
    Update safety documentation and Hall safety walkthrough to become
    as generic as possible for all Halls (A-D)
    COO generic document
    ESAD generic format (draft)
    RSAD generic format
    Safety checklists
    Experimental procedures for users (wiki or “how-to’s”)
    Operations Manual for experts
    Safety Walkthroughs generic format (draft)
    - Include decommissioning in reviews
RICH comes in at “2nd readiness review”: review before scheduling request