## Slide 1: CLAS12-RICH Project-Status & Tasks Towards Completion
June 13th 2016
Charge 3:
Has the detector been completed towards operation? If not, what are the completion/commissioning schedule and tasks?

## Slide 2
Project Milestones
2
CLAS12 RiCH Readiness Review, 13th June 2016

## Slide 3
Mechanics
3
Assembling test ongoing in Italy
Delivery expected before the summer
Next:
- Closing panel (Argonne)
- Cart and joints for Installation (LNF)
3m diameter autoclave housing large panels
CFRP Reinforcing Ribs
CFRP Top Panel
CLAS12 RiCH Readiness Review, 13th June 2016

## Slide 4
Aerogel
4
<Lsc> ~ 50 mm
A0 > 95 %
3 cm layers:
Production tiles fulfill specifications
Tile delivery proceeds steadily
36 tiles out of foreseen 72 approved
Next: start 2cm layer production
CLAS12 RiCH Readiness Review, 13th June 2016
All tiles are measured at the production
site (Novosibirsk) before delivery approval.
Acceptance tests at JLab and CUA.
Stress tests and optical study at Ferrara.
Laser bench @ FE for
specific light propagation
Tests (FS, double passage)
Same spectrophotometer with
large sample compartment
available @ FE and CUA.

## Slide 5
5
Spherical Mirrors
Reflected image comparable
with the 1 mm source size
and stable over time
Surface analyzer
(waveform sensor)
Spot image sensor
(point-like source)
Mechanical guide
(along optical axis)
Produced at CMA (Tucson, AZ)
4 Mirror delivered (out of 10)
Surface accuracy better than specifications
Areal density better than LHC-b
Next (LNF):
- Mockup for assembling
- Support structure
CLAS12 RiCH Readiness Review, 13th June 2016

## Slide 6
6
Planar Mirrors
Produced at Media-Lario (Bosisio Parini, Italy)
2 Mirror produced (out of 7)
Surface accuracy better than specifications
Reflectivity fulfilling specifications
Next (LNF):
- Validate aerogel assembling procedure
CLAS12 RiCH Readiness Review, 13th June 2016

## Slide 7
7
MA-PMT Photon Detector
H8500
H12700
Full characterization done on a pulsed-laser bench
All MA-PMTs delivered
2 out of 391 rejected and substituted
Stand-alone characterization done
Storing info into CLAS12 database (JLab/DU)
Next (FE + JLab):
- Characterization with RICH electronics
CLAS12 RiCH Readiness Review, 13th June 2016
Notes: Ricordarsi quanti sono gli h8500

## Slide 8
8
Electronics
FPGA:
- Production done
- Stand-alone validation done
Asics+Adapter
- Pre-production done
- Stand-alone validation done
- All MAROC3A chips delivered
Succesfully Test-Beam @ Fermilab
Next (FE):
- Complete production before summer
CLAS12 RiCH Readiness Review, 13th June 2016

## Slide 9
9
Electronics
Preliminary Tests Done
Developing characterization procedures
Next (FE + JLab):
- Characterization with MA-PMTs
- Store relevant information on CLAS12
database
CLAS12 RiCH Readiness Review, 13th June 2016
Time resolution with pulsed laser
Noise, single (photo)-electron signal

## Slide 10
Services: Powers and DAQ
10
SY4527 LV & HV Power Supply
(compatible with EPICS)
5 SSP Fiber-Optic DAQ
(compatible with CLAS12)
LV
HV
Service
Loglines
CLAS12 RiCH Readiness Review, 13th June 2016
Notes: Qua mi fanno il culo di sicuro sui LV.

## Slide 11
Services: Backend Electronics
11
CLAS12 RiCH Readiness Review, 13th June 2016

## Slide 12
Services: Gas Systems
12
CLAS12 RiCH Readiness Review, 13th June 2016
RICH Cooling Circuit
Diagram with Interlock
(G. Jacobs)
RICH N2 Pure Gas
System Diagram
(G. Jacobs)
To electronics

## Slide 13
13
Software
Slow Control:
Basic hardware supported by CLAS12
- SY4527 power supply
- cRio for gas systems
SSP will provide temperature and
bias voltages for all chips
Next: Implementation within CLAS12
Reconstruction:
Full chain under development:
- gemc simulation
- coatjava based reconstruction
- java based event display
Next:
Optimize for KPP
DAQ and Calibration:
- Tested on PCI-e optical link
Next: SSP and CODA
CLAS12 RiCH Readiness Review, 13th June 2016

## Slide 14
14
Tasks Toward Completion
CLAS12 RiCH Readiness Review, 13th June 2016
Component production organized subject to assembling schedule
Critical path: 4 months
contingency included

## Slide 15
15
CLAS12 RICH Status
✔ Components
- Under production
- Performance in line or better than the design specification
- Deliveries organized subject to assembling schedule
✔ Assembling & Installation
- Start foreseen in October 2016
- Almost 1 year before installation
- Comprises commissioning of all systems without beam
✔ Operation
- Hazard identified
- Services defined to be compatible with CLAS12
- Slow control and Interlock under development
- Reconstruction software under development
CLAS12 RiCH Readiness Review, 13th June 2016