## Slide 1: CLAS12-RICH
INFN(Italy), Jlab,
Argonne National Lab, Duquesne University,
Kyungpook National University (Republic of Korea),
J. Gutenberg Universitat Mainz (Germany),
Universidad Tecnica Federico Santa Maria (Chile),
University of Connecticut, University of Glasgow (UK)
1st sector construction started in September 2013
RICH Module mechanics ready for review by JLab engineers
Procurement of F-E board prototypes initiated
First mirror demos delivered
First large aerogel tile (20x20 cm2)
demos delivered

## Slide 2
90 Hamamatsu MAPMT out of 400 delivered and tested at Jlab
80 H8500
10 H12700 with enhanced single photoelectron spectrum
Jlab Test Stand
H8500
Single Photoelectron Spectrum
H12700
FADC counts
PMT Gain Comparison:
Hamamatsu Jlab
Pixel Number
MAPMT characterization

## Slide 3: RICH Construction Schedule
Milestone | Date
Concept of Design and Technology | 2010
Tests of components and small prototype | 2011
Test-beam with electrons (Frascati) and hadrons (CERN) | 2012-2013
Start Engineering Phase | Feb. 2013
Hall-B review | June 2013
TDR | Aug. 2013
Physics Division review with DOE observers | Sep. 2013
Hamamatsu contract awarded | 30 Sep. 2013
Electronics boards completed | July 2015
MA-PMT production completed | Dec. 2015
Mirror production completed | Sep. 2015
Start RICH assembly | Oct. 2016
Aerogel production completed | Dec. 2016
RICH project completed | June 2017