## Slide 1
RICH Detector
Hall B
CLAS12
Spherical mirrors:
- All 10 mirrors accepted
- Back to vendor to build support and alignment structure
Mechanical structure
- Assembling at JLab ongoing with the help of the DSG
- Support structure for the electronics panel arrived to Jlab
Planar mirrors:
- 3/5 lateral mirrors accepted
- 2 front mirrors in production
22/03/17
1
CLAS collaboration meeting, JLab 11/01-04
Electronics panel with support ready at Jlab
RICH structure assembled at Jlab!

## Slide 2
RICH Detector
Hall B
CLAS12
Electronics:
All electronics front-end boards are at JLab
Acceptance tests done at the company
- Electronics boards characterization ongoing
- s(ped)/1phe ~ 1%
Aerogel:
- Five additional 3cm tiles delivered in January and tested (got >75% of the minimum quantity required)
- 2cm layer production started
22/03/17
2
CLAS collaboration meeting, JLab 11/01-04
One photoelectron spectrum
taken with new front-end
Slow Control design ongoing
Digital time walk correction
On schedule for the installation in Hall B in September 2017